## Antes y Después
Action Test Plan |  |  | Alvaro Navarro |  | Proyecto
CAF - Upgrade Venezuela (GWVESM-1) |  |  |  |  | VE.197.019
Global Test Type | Specific Test Type | Status | When | Who | Notes
Unified Communications
Registro de dispositivos | Registro de telefonos | To Do | Pre-Cut | Soutec
Llamadas a la PSTN | Cel (004128018274), Casa Caracas (09446063) | To Do | Pre-Cut | Soutec
DTMF | Tonos DTMF Salientes | To Do | Pre-Cut | Soutec
Llamadas Entrantes | Numero principal | To Do | Pre-Cut | Soutec
Pruebas de SRST | Registro de telefonos | To Do | Pre-Cut | Soutec
| Llamadas salientes Cel (0915117772), Hotel Lima (03155000) | To Do | Pre-Cut | Soutec
| Llamadas entrantes numero principal | To Do | Pre-Cut | Soutec
Routing
| Ping Gateway VOIP GWVESM-1 | To Do | Pre-Cut | Soutec | Ping 10.200.16.4
| Ping Gateway VOIP GWVESM-2 | To Do | Pre-Cut | Soutec | Ping 10.200.16.5
EIGRP | Validacion de vecindades EIGRP | To Do | Pre-Cut | Soutec | Show ip eigrp topology, Show ip eigrp neighbors
| Validacion de tabla de enrutamiento EIGRP | To Do | Pre-Cut | Soutec | Show ip route eigrp
| Validacion de interfaces EIGRP | To Do | Pre-Cut | Soutec | Show ip eigrp interfaces
RIP | Validacion de protocolo RIP | To Do | Pre-Cut | Soutec | Show ip protocols
| Validacion de tabla de enrutamiento RIP | To Do | Pre-Cut | Soutec | Show ip route rip
WAN | Gateway WAN | To Do | Pre-Cut | Soutec | Ping 208.51.150.49
Comportamiento del equipo | Consumo de CPU | To Do | Pre-Cut | Soutec | Show processes cpu sorted
Validacion SLA's | Validacion de SLA's configurados | To Do | Pre-Cut | Soutec | Show ip sla summary
AAA
TACACS+ | Verificar conectividad contra TACACS+ | To Do | Pre-Cut | Soutec | ping 10.1.0.80 (NAP) - 10.8.0.80 (CCS)
| Verificar autenticacion con TACACS+ | To Do | Pre-Cut | CAF | autenticacion via tacacs+ por CAF
SSH
SSH | Verificar conexión via SSH | To Do | Pre-Cut | CAF | Conectarse via ssh al dispositivo
NTP
NTP | Verificar conectividad contra servidor NTP | To Do | Pre-Cut | Soutec | Ping 10.1.11.1
| Validar hora del dispositivo | To Do | Pre-Cut | Soutec | Show clock, Show ntp status
Note on F20: Robert Aznar: Es probable que el ping no responda

## Durante
Action Test Plan |  |  | Robert Aznar |  | Proyecto
CAF - Upgrade Perú (RPESM-1) |  |  |  |  | VE.197.019
Global Test Type | Specific Test Type | Estado | Cuando | Quien | Notas
Pruebas ICMP
Interfaz LAN | Ping extendido durante el upgrade interfaz LAN | To Do | Durante |  | Ping 10.13.0.2